## S-Curve (2) (hidden)
Year | 2025 | [38 empty] | 2026
Quarter | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1
Month | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | June | June | June | June | July | July | July
Week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60 | W61 | W62 | W63 | W64 | W65 | W66 | W67 | W67
Plan Weekly % | 0.2922% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0.6573% | 0.4904% | 0.6573% | 0.6573% | 0.6573% | 0.6365% | 2.598% | 2.061% | 1.972% | 1.956% | 1.972% | 1.972% | 1.972% | 1.972% | 1.8% | 1.941% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 6.375% | 6.62% | 4.382% | 3.871% | 6.579% | 6.506% | 6.156% | 5.212% | 3.918% | 2.838% | 2.207% | 1.753% | 0.2922%
Actual Weekly % | 0.2922% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0.6573% | 0.4904% | 0.6573% | 0.6573% | 0.7878% | 0.1628% | 0.4633% | 0.5008% | 0.5676% | 0.1002% | 0.24% | 0.2692% | 0.1482% | 0.2087% | 0.1043% | 0.2609% | 0.1252% | 0.08347% | 0.4695% | 1.972% | 0.9349% | 1.194% | 1.448% | 0.9683% | 0.2963% | 0.2963% | 1.177% | 2.917% | 0.8723% | 4.067% | 1.654% | 1.397% | 1.831% | 0.1% | 1.273% | 2.295% | 0.8372% | 1% | 1% | 0.5987% | 3.993% | 4.238% | 3.263% | 0.788% | 1.372% | 1.004% | 1.166% | 0.7304% | 0.7846% | 1.062% | 0.52% | 0.3005% | 1.143% | 0.3088% | 0.5008%
Plan Accum % | 0.2922% | 0.7095% | 1.127% | 1.544% | 1.962% | 2.379% | 2.796% | 3.214% | 3.631% | 4.048% | 4.466% | 4.883% | 5.514% | 6.172% | 6.662% | 7.319% | 7.977% | 8.634% | 9.271% | 11.87% | 13.93% | 15.9% | 17.86% | 19.83% | 21.8% | 23.77% | 25.75% | 27.55% | 29.49% | 31.46% | 33.43% | 35.4% | 37.37% | 39.35% | 41.32% | 43.29% | 49.67% | 56.29% | 60.67% | 64.54% | 71.12% | 77.62% | 83.78% | 88.99% | 92.91% | 95.75% | 97.95% | 99.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Actual Accum % | 0.2922% | 0.7095% | 1.127% | 1.544% | 1.962% | 2.379% | 2.796% | 3.214% | 3.631% | 4.048% | 4.466% | 4.883% | 5.514% | 6.172% | 6.662% | 7.319% | 7.977% | 8.765% | 8.927% | 9.391% | 9.891% | 10.46% | 10.56% | 10.8% | 11.07% | 11.22% | 11.43% | 11.53% | 11.79% | 11.92% | 12% | 12.47% | 14.44% | 15.38% | 16.57% | 18.02% | 18.99% | 19.28% | 19.58% | 20.76% | 23.67% | 24.55% | 28.61% | 30.27% | 31.66% | 33.49% | 33.59% | 34.87% | 37.16% | 38% | 39% | 40% | 40.6% | 44.59% | 48.83% | 52.09% | 52.88% | 54.25% | 55.26% | 56.42% | 57.15% | 57.94% | 59% | 59.52% | 59.82% | 60.96% | 61.27% | 61.77%
Variance | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -0.1304% | 0.3433% | 2.478% | 4.038% | 5.442% | 7.299% | 9.031% | 10.73% | 12.56% | 14.32% | 16.02% | 17.7% | 19.54% | 21.43% | 22.93% | 22.93% | 23.97% | 24.75% | 25.27% | 30.68% | 37% | 41.09% | 43.78% | 47.45% | 53.08% | 55.17% | 58.73% | 61.25% | 62.25% | 64.36% | 64.84% | 62.84% | 62% | 61% | 60% | 59.4% | 55.41% | 51.17% | 47.91% | 47.12% | 45.75% |  | 43.58%
Catch up Plan | bar: Q1 May W58 to Q1 July W67

## S-Curve Baseline 1
Year | 2025 | [38 empty] | 2026
Quarter | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1
Month | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | June | June | June | June | July | July | July
Week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60 | W61 | W62 | W63 | W64 | W65 | W66 | W67 | W67
Plan Weekly % | 0.2922% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0.6573% | 0.4904% | 0.6573% | 0.6573% | 0.6573% | 0.6365% | 2.598% | 2.061% | 1.972% | 1.956% | 1.972% | 1.972% | 1.972% | 1.972% | 1.8% | 1.941% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 6.375% | 6.62% | 4.382% | 3.871% | 6.579% | 6.506% | 6.156% | 5.212% | 3.918% | 2.838% | 2.207% | 1.753% | 0.2922%
Actual Weekly % | 0.2922% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0.6573% | 0.4904% | 0.6573% | 0.6573% | 0.7878% | 0.1628% | 0.4633% | 0.5008% | 0.5676% | 0.1002% | 0.24% | 0.2692% | 0.1482% | 0.2087% | 0.1043% | 0.2609% | 0.1252% | 0.08347% | 0.4695% | 1.972% | 0.9349% | 1.194% | 1.448% | 0.9683% | 0.2963% | 0.2963% | 1.177% | 2.917% | 0.8723% | 4.067% | 1.654% | 1.397% | 1.831% | 0.1% | 1.273% | 2.295% | 0.8372% | 1% | 1% | 0.5987% | 3.993% | 4.238% | 3.263% | 0.788% | 1.372% | 1.004% | 1.166% | 0.7304% | 0.7846% | 1.062% | 0.52% | 0.3005% | 1.143% | 0.3088% | 0.5008%
Plan Accum % | 0.2922% | 0.7095% | 1.127% | 1.544% | 1.962% | 2.379% | 2.796% | 3.214% | 3.631% | 4.048% | 4.466% | 4.883% | 5.514% | 6.172% | 6.662% | 7.319% | 7.977% | 8.634% | 9.271% | 11.87% | 13.93% | 15.9% | 17.86% | 19.83% | 21.8% | 23.77% | 25.75% | 27.55% | 29.49% | 31.46% | 33.43% | 35.4% | 37.37% | 39.35% | 41.32% | 43.29% | 49.67% | 56.29% | 60.67% | 64.54% | 71.12% | 77.62% | 83.78% | 88.99% | 92.91% | 95.75% | 97.95% | 99.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Actual Accum % | 0.2922% | 0.7095% | 1.127% | 1.544% | 1.962% | 2.379% | 2.796% | 3.214% | 3.631% | 4.048% | 4.466% | 4.883% | 5.514% | 6.172% | 6.662% | 7.319% | 7.977% | 8.765% | 8.927% | 9.391% | 9.891% | 10.46% | 10.56% | 10.8% | 11.07% | 11.22% | 11.43% | 11.53% | 11.79% | 11.92% | 12% | 12.47% | 14.44% | 15.38% | 16.57% | 18.02% | 18.99% | 19.28% | 19.58% | 20.76% | 23.67% | 24.55% | 28.61% | 30.27% | 31.66% | 33.49% | 33.59% | 34.87% | 37.16% | 38% | 39% | 40% | 40.6% | 44.59% | 48.83% | 52.09% | 52.88% | 54.25% | 55.26% | 56.42% | 57.15% | 57.94% | 59% | 59.52% | 59.82% | 60.96% | 61.27% | 61.77%
Variance | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -0.1304% | 0.3433% | 2.478% | 4.038% | 5.442% | 7.299% | 9.031% | 10.73% | 12.56% | 14.32% | 16.02% | 17.7% | 19.54% | 21.43% | 22.93% | 22.93% | 23.97% | 24.75% | 25.27% | 30.68% | 37% | 41.09% | 43.78% | 47.45% | 53.08% | 55.17% | 58.73% | 61.25% | 62.25% | 64.36% | 64.84% | 62.84% | 62% | 61% | 60% | 59.4% | 55.41% | 51.17% | 47.91% | 47.12% | 45.75% |  | 43.58%
Catch up Plan | bar: Q1 May W58 to Q1 July W67

## S-Curve Baseline 2
| 2025 | [40 empty] | 2026
| Q2 | [12 empty] | Q3 | [13 empty] | Q4 | [13 empty] | Q1 | [13 empty] | Q2 | [13 empty] | Q3 | [13 empty] | Q4
Month | April | April | April | May | May | May | May | May | June | June | June | June | July | July | July | July | July | August | August | August | August | August | September | September | September | September | October | October | October | October | October | November | November | November | November | November | December | December | December | December | January | January | January | January | January | January | February | February | February | February | March | March | March | March | March | April | April | April | April | May | May | May | May | May | June | June | June | June | July | July | July | July | July | August | August | August | August | August | October | October | October | October | October | October | October | October | October | October | November | November | November | November | November
Week | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 1 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36
Planned Weekly | 0.2922% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0.6573% | 0.4904% | 0.6573% | 0.6573% | 0.6573% | 0.6365% | 2.598% | 2.061% | 1.972% | 1.956% | 1.972% | 1.972% | 1.972% | 1.972% | 1.8% | 1.941% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 6.375% | 6.62% | 4.382% | 3.871% | 6.579% | 6.506% | 6.156% | 5.212% | 3.918% | 2.838% | 2.207% | 1.753% | 0.2922% | [23 empty] | 4.116% | 5.037% | 4.955% | 4.095% | 3.276% | 2.94% | 2.252% | 1.458% | 0.819% | 1.057% | 0.6552% | 0.3276% | 0.819% | 0.6634% | 1.179% | 1.229% | 0.8436% | 0.819% | 0.819% | 0.819% | 0.04914%
Actual Weekly | 0% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0% | 1.148% | 0.6573% | 0.6573% | 0.7878% | 0.1628% | 0.4633% | 0.5008% | 0.5676% | 0.1002% | 0.24% | 0.2692% | 0.1482% | 0.2087% | 0% | 0.1043% | 0.2609% | 0.1252% | 0.08347% | 0.4695% | 1.972% | 0.9349% | 1.194% | 1.448% | 0.9683% | 0.2963% | 0.2963% | 1.177% | 0% | 2.917% | 0.8723% | 4.067% | 1.654% | 1.397% | 1.831% | 0.1% | 1.273% | 2.295% | 0.8372% | 1% | 1% | 0.5987% | 0% | 3.993% | 4.238% | 3.263% | 0.788% | 1.372% | 1.004% | 1.166% | 0.7304% | 0.7846% | 1.062% | 0.52% | 0.3005% | 1.143% | 0% | 0.3088% | 0.5008% | 0.2679% | 0.3923% | 0.3172%
Baseline | Q2 April Week 2: 28; Q2 April Week 3: 68; Q2 April Week 4: 108; Q2 May Week 5: 148; Q2 May Week 6: 188; Q2 May Week 7: 228; Q2 May Week 8: 268; Q2 May Week 9: 308; Q2 June Week 10: 348; Q2 June Week 11: 388; Q2 June Week 12: 428; Q2 June Week 13: 468; Q2 July Week 14: 476; Q3 July Week 14: 528.5; Q3 July Week 15: 591.5; Q3 July Week 16: 638.5; Q3 July Week 17: 701.5; Q3 August Week 18: 764.5; Q3 August Week 19: 827.5; Q3 August Week 20: 888.5; Q3 August Week 21: 1137.5; Q3 August Week 22: 1335; Q3 September Week 23: 1524; Q3 September Week 24: 1711.5; Q3 September Week 25: 1900.5; Q3 September Week 26: 2089.5; Q3 October Week 27: 2152.5; Q4 October Week 27: 2278.5; Q4 October Week 28: 2467.5; Q4 October Week 29: 2640; Q4 October Week 30: 2826; Q4 November Week 31: 3015; Q4 November Week 32: 3204; Q4 November Week 33: 3393; Q4 November Week 34: 3582; Q4 November Week 35: 3771; Q4 December Week 36: 3960; Q4 December Week 37: 4149; Q4 December Week 38: 4760; Q4 December Week 39: 5394.5; Q4 January Week 40: 5814.5; Q1 January Week 40: 6185.5; Q1 January Week 41: 6816; Q1 January Week 42: 7439.5; Q1 January Week 43: 8029.5; Q1 January Week 44: 8529; Q1 February Week 45: 8904.5; Q1 February Week 46: 9176.5; Q1 February Week 47: 9388; Q1 February Week 48: 9556; Q1 March Week 49: 9768
Baseline #2 | 28 | 68 | 108 | 148 | 188 | 228 | 268 | 308 | 348 | 388 | 428 | 468 | 476 | 528.5 | 591.5 | 638.5 | 701.5 | 764.5 | 827.5 | 888.5 | 1036 | 1224 | 1413 | 1552.5 | 1741.5 | 1930.5 | 1984.2 | 2068.2 | 2194.2 | 2298.2 | 2499.6 | 2688.6 | 2877.6 | 3007.6 | 3133.6 | 3259.6 | 3385.6 | 3487.6 | 3911.6 | 4334.1 | 4602.2 | 4804.5 | 5091.5 | 5347.32 | 5549.82 | 5758.82 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 6436 | 6928 | 7412 | 7812 | 8132 | 8419.2 | 8639.2 | 8781.6 | 8861.6 | 8964.8 | 9028.8 | 9060.8 | 9140.8 | 9205.6 | 9320.8 | 9440.8 | 9523.2 | 9603.2 | 9683.2 | 9763.2 | 9768
Baseline % Accu. | Q2 April Week 2: 0.2867%; Q2 April Week 3: 0.6962%; Q2 April Week 4: 1.106%; Q2 May Week 5: 1.515%; Q2 May Week 6: 1.925%; Q2 May Week 7: 2.334%; Q2 May Week 8: 2.744%; Q2 May Week 9: 3.153%; Q2 June Week 10: 3.563%; Q2 June Week 11: 3.972%; Q2 June Week 12: 4.382%; Q2 June Week 13: 4.791%; Q2 July Week 14: 4.873%; Q3 July Week 14: 5.411%; Q3 July Week 15: 6.055%; Q3 July Week 16: 6.537%; Q3 July Week 17: 7.182%; Q3 August Week 18: 7.827%; Q3 August Week 19: 8.472%; Q3 August Week 20: 9.096%; Q3 August Week 21: 11.65%; Q3 August Week 22: 13.67%; Q3 September Week 23: 15.6%; Q3 September Week 24: 17.52%; Q3 September Week 25: 19.46%; Q3 September Week 26: 21.39%; Q3 October Week 27: 22.04%; Q4 October Week 27: 23.33%; Q4 October Week 28: 25.26%; Q4 October Week 29: 27.03%; Q4 October Week 30: 28.93%; Q4 November Week 31: 30.87%; Q4 November Week 32: 32.8%; Q4 November Week 33: 34.74%; Q4 November Week 34: 36.67%; Q4 November Week 35: 38.61%; Q4 December Week 36: 40.54%; Q4 December Week 37: 42.48%; Q4 December Week 38: 48.73%; Q4 December Week 39: 55.23%; Q4 January Week 40: 59.53%; Q1 January Week 40: 63.32%; Q1 January Week 41: 69.78%; Q1 January Week 42: 76.16%; Q1 January Week 43: 82.2%; Q1 January Week 44: 87.32%; Q1 February Week 45: 91.16%; Q1 February Week 46: 93.94%; Q1 February Week 47: 96.11%; Q1 February Week 48: 97.83%; Q1 March Week 49: 100%
Baseline #2 % Accu. | Q3 July Week 16: 61.77%; Q3 July Week 17: 65.89%; Q3 August Week 18: 70.93%; Q3 August Week 19: 75.88%; Q3 August Week 20: 79.98%; Q3 August Week 21: 83.25%; Q3 August Week 22: 86.19%; Q3 October Week 23: 88.44%; Q3 October Week 24: 89.9%; Q3 October Week 25: 90.72%; Q3 October Week 26: 91.78%; Q3 October Week 27: 92.43%; Q4 October Week 27: 92.76%; Q4 October Week 28: 93.58%; Q4 October Week 29: 94.24%; Q4 October Week 30: 95.42%; Q4 October Week 31: 96.65%; Q4 November Week 32: 97.49%; Q4 November Week 33: 98.31%; Q4 November Week 34: 99.13%; Q4 November Week 35: 99.95%; Q4 November Week 36: 100%
Actual Accu. | 0.2922% | 0.7095% | 1.127% | 1.544% | 1.962% | 2.379% | 2.796% | 3.214% | 3.631% | 4.048% | 4.466% | 4.883% | 5.514% | 5.514% | 6.662% | 7.319% | 7.977% | 8.765% | 8.927% | 9.391% | 9.891% | 10.46% | 10.56% | 10.8% | 11.07% | 11.22% | 11.43% | 11.43% | 11.53% | 11.79% | 11.92% | 12% | 12.47% | 14.44% | 15.38% | 16.57% | 18.02% | 18.99% | 19.28% | 19.58% | 20.76% | 20.76% | 23.67% | 24.55% | 28.61% | 30.27% | 31.66% | 33.49% | 33.59% | 34.87% | 37.16% | 38% | 39% | 40% | 40.6% | 40.6% | 44.59% | 48.83% | 52.09% | 52.88% | 54.25% | 55.26% | 56.42% | 57.15% | 57.94% | 59% | 59.52% | 59.82% | 60.96% | 60.96% | 61.27% | 61.77% | 62.04%
Variance | Q2 April Week 2: -0.005503%; Q2 April Week 3: -0.01337%; Q2 April Week 4: -0.02123%; Q2 May Week 5: -0.02909%; Q2 May Week 6: -0.03695%; Q2 May Week 7: -0.04481%; Q2 May Week 8: -0.05267%; Q2 May Week 9: -0.06054%; Q2 June Week 10: -0.0684%; Q2 June Week 11: -0.07626%; Q2 June Week 12: -0.08412%; Q2 June Week 13: -0.09198%; Q2 July Week 14: -0.6413%; Q3 July Week 14: -0.1039%; Q3 July Week 15: -0.6067%; Q3 July Week 16: -0.7828%; Q3 July Week 17: -0.7952%; Q3 August Week 18: -0.938%; Q3 August Week 19: -0.4558%; Q3 August Week 20: -0.2946%; Q3 August Week 21: 1.754%; Q3 August Week 22: 3.208%; Q3 September Week 23: 5.043%; Q3 September Week 24: 6.722%; Q3 September Week 25: 8.388%; Q3 September Week 26: 10.17%; Q3 October Week 27: 10.61%; Q4 October Week 27: 11.9%; Q4 October Week 28: 13.73%; Q4 October Week 29: 15.24%; Q4 October Week 30: 17.02%; Q4 November Week 31: 18.87%; Q4 November Week 32: 20.33%; Q4 November Week 33: 20.3%; Q4 November Week 34: 21.3%; Q4 November Week 35: 22.04%; Q4 December Week 36: 22.52%; Q4 December Week 37: 23.49%; Q4 December Week 38: 29.45%; Q4 December Week 39: 35.65%; Q4 January Week 40: 38.77%; Q1 January Week 40: 42.57%; Q1 January Week 41: 46.11%; Q1 January Week 42: 51.62%; Q1 January Week 43: 53.59%; Q1 January Week 44: 57.05%; Q1 February Week 45: 59.5%; Q1 February Week 46: 60.45%; Q1 February Week 47: 62.52%; Q1 February Week 48: 62.96%; Q1 March Week 49: 62.84%; Q3 July Week 16: 0%; Q3 July Week 17: 3.848%
Current week highligter | Q3 July Week 16: 100%

## S-Curve Baseline 2 HIDE (hidden)
| 2025 | [40 empty] | 2026
| Q2 | [12 empty] | Q3 | [13 empty] | Q4 | [13 empty] | Q1 | [13 empty] | Q2 | [13 empty] | Q3 | [13 empty] | Q4
Month
| Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 1 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31
Planned Weekly | 0.2922% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0.6573% | 0.4904% | 0.6573% | 0.6573% | 0.6573% | 0.6365% | 2.598% | 2.061% | 1.972% | 1.956% | 1.972% | 1.972% | 1.972% | 1.972% | 1.8% | 1.941% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 6.375% | 6.62% | 4.382% | 3.871% | 6.579% | 6.506% | 6.156% | 5.212% | 3.918% | 2.838% | 2.207% | 1.753% | 0.2922% | [19 empty] | 4.116% | 5.037% | 4.955% | 4.095% | 3.276% | 2.94% | 2.252% | 1.458% | 0.819% | 1.057% | 0.9828% | 0.819% | 0.6634% | 1.179% | 1.229% | 0.8436% | 0.819% | 0.819% | 0.819%
Actual Weekly | 0.2922% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0.6573% | 0.4904% | 0.6573% | 0.6573% | 0.7878% | 0.1628% | 0.4633% | 0.5008% | 0.5676% | 0.1002% | 0.24% | 0.2692% | 0.1482% | 0.2087% | 0.1043% | 0.2609% | 0.1252% | 0.08347% | 0.4695% | 1.972% | 0.9349% | 1.194% | 1.448% | 0.9683% | 0.2963% | 0.2963% | 1.177% | 2.917% | 0.8723% | 4.067% | 1.654% | 1.397% | 1.831% | 0.1% | 1.273% | 2.295% | 0.8372% | 1% | 1% | 0.5987% | 3.993% | 4.238% | 3.263% | 0.788% | 1.372% | 1.004% | 1.166% | 0.7304% | 0.7846% | 1.062% | 0.52% | 0.3005% | 1.143% | 0.3088% | 0.5008%
Baseline | Week 2: 28; Week 3: 68; Week 4: 108; Week 5: 148; Week 6: 188; Week 7: 228; Week 8: 268; Week 9: 308; Week 10: 348; Week 11: 388; Week 12: 428; Week 13: 468; Week 14: 476; Week 14: 528.5; Week 15: 591.5; Week 16: 638.5; Week 17: 701.5; Week 18: 764.5; Week 19: 827.5; Week 20: 888.5; Week 21: 1137.5; Week 22: 1335; Week 23: 1524; Week 24: 1711.5; Week 25: 1900.5; Week 26: 2089.5; Week 27: 2152.5; Week 27: 2278.5; Week 28: 2467.5; Week 29: 2640; Week 30: 2826; Week 31: 3015; Week 32: 3204; Week 33: 3393; Week 34: 3582; Week 35: 3771; Week 36: 3960; Week 37: 4149; Week 38: 4760; Week 39: 5394.5; Week 40: 5814.5; Week 40: 6185.5; Week 41: 6816; Week 42: 7439.5; Week 43: 8029.5; Week 44: 8529; Week 45: 8904.5; Week 46: 9176.5; Week 47: 9388; Week 48: 9556; Week 49: 9768
Baseline #2 | 28 | 68 | 108 | 148 | 188 | 228 | 268 | 308 | 348 | 388 | 428 | 468 | 528.5 | 591.5 | 638.5 | 701.5 | 764.5 | 827.5 | 888.5 | 1036 | 1224 | 1413 | 1552.5 | 1741.5 | 1930.5 | 2068.2 | 2194.2 | 2298.2 | 2499.6 | 2688.6 | 2877.6 | 3007.6 | 3133.6 | 3259.6 | 3385.6 | 3487.6 | 3911.6 | 4334.1 | 4602.2 | 4804.5 | 5091.5 | 5347.32 | 5549.82 | 5758.82 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 6436 | 6928 | 7412 | 7812 | 8132 | 8419.2 | 8639.2 | 8781.6 | 8861.6 | 8964.8 | 9060.8 | 9140.8 | 9205.6 | 9320.8 | 9440.8 | 9523.2 | 9603.2 | 9683.2 | 9763.2 | 9768
Baseline % | Week 2: 0.2867%; Week 3: 0.6962%; Week 4: 1.106%; Week 5: 1.515%; Week 6: 1.925%; Week 7: 2.334%; Week 8: 2.744%; Week 9: 3.153%; Week 10: 3.563%; Week 11: 3.972%; Week 12: 4.382%; Week 13: 4.791%; Week 14: 4.873%; Week 14: 5.411%; Week 15: 6.055%; Week 16: 6.537%; Week 17: 7.182%; Week 18: 7.827%; Week 19: 8.472%; Week 20: 9.096%; Week 21: 11.65%; Week 22: 13.67%; Week 23: 15.6%; Week 24: 17.52%; Week 25: 19.46%; Week 26: 21.39%; Week 27: 22.04%; Week 27: 23.33%; Week 28: 25.26%; Week 29: 27.03%; Week 30: 28.93%; Week 31: 30.87%; Week 32: 32.8%; Week 33: 34.74%; Week 34: 36.67%; Week 35: 38.61%; Week 36: 40.54%; Week 37: 42.48%; Week 38: 48.73%; Week 39: 55.23%; Week 40: 59.53%; Week 40: 63.32%; Week 41: 69.78%; Week 42: 76.16%; Week 43: 82.2%; Week 44: 87.32%; Week 45: 91.16%; Week 46: 93.94%; Week 47: 96.11%; Week 48: 97.83%; Week 49: 100%
Baseline #2 % | Week 13: 61.77%; Week 14: 65.89%; Week 14: 70.93%; Week 15: 75.88%; Week 16: 79.98%; Week 17: 83.25%; Week 18: 86.19%; Week 19: 88.44%; Week 20: 89.9%; Week 21: 90.72%; Week 22: 91.78%; Week 23: 92.76%; Week 24: 93.58%; Week 25: 94.24%; Week 26: 95.42%; Week 27: 96.65%; Week 27: 97.49%; Week 28: 98.31%; Week 29: 99.13%; Week 30: 99.95%; Week 31: 100%
Actual | 0.2922% | 0.7095% | 1.127% | 1.544% | 1.962% | 2.379% | 2.796% | 3.214% | 3.631% | 4.048% | 4.466% | 4.883% | 5.514% | 6.172% | 6.662% | 7.319% | 7.977% | 8.765% | 8.927% | 9.391% | 9.891% | 10.46% | 10.56% | 10.8% | 11.07% | 11.22% | 11.43% | 11.53% | 11.79% | 11.92% | 12% | 12.47% | 14.44% | 15.38% | 16.57% | 18.02% | 18.99% | 19.28% | 19.58% | 20.76% | 23.67% | 24.55% | 28.61% | 30.27% | 31.66% | 33.49% | 33.59% | 34.87% | 37.16% | 38% | 39% | 40% | 40.6% | 44.59% | 48.83% | 52.09% | 52.88% | 54.25% | 55.26% | 56.42% | 57.15% | 57.94% | 59% | 59.52% | 59.82% | 60.96% | 61.27% | 61.77%
Variance | bar: Week 13

## S-Curve Baseline2 July-Nov 26
| 2025 | [40 empty] | 2026
| Q2 | [12 empty] | Q3 | [13 empty] | Q4 | [13 empty] | Q1 | [13 empty] | Q2 | [13 empty] | Q3 | [13 empty] | Q4
Month | April | April | April | May | May | May | May | May | June | June | June | June | July | July | July | July | July | August | August | August | August | August | September | September | September | September | October | October | October | October | October | November | November | November | November | November | December | December | December | December | January | January | January | January | January | January | February | February | February | February | March | March | March | March | March | April | April | April | April | May | May | May | May | May | June | June | June | June | July | July | July | July | July | August | August | August | August | August | September | September | September | September | September | October | October | October | October | October | November | November | November | November | November
Week | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 1 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36
Planned Weekly | 0.2922% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0.6573% | 0.4904% | 0.6573% | 0.6573% | 0.6573% | 0.6365% | 2.598% | 2.061% | 1.972% | 1.956% | 1.972% | 1.972% | 1.972% | 1.972% | 1.8% | 1.941% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 1.972% | 6.375% | 6.62% | 4.382% | 3.871% | 6.579% | 6.506% | 6.156% | 5.212% | 3.918% | 2.838% | 2.207% | 1.753% | 0.2922% | [23 empty] | 4.116% | 5.037% | 4.955% | 4.095% | 3.276% | 2.94% | 2.252% | 1.458% | 0.819% | 1.057% | 0.6552% | 0.3276% | 0.819% | 0.6634% | 1.179% | 1.229% | 0.8436% | 0.819% | 0.819% | 0.819% | 0.04914%
Actual Weekly | 0% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.4174% | 0.6313% | 0% | 1.148% | 0.6573% | 0.6573% | 0.7878% | 0.1628% | 0.4633% | 0.5008% | 0.5676% | 0.1002% | 0.24% | 0.2692% | 0.1482% | 0.2087% | 0% | 0.1043% | 0.2609% | 0.1252% | 0.08347% | 0.4695% | 1.972% | 0.9349% | 1.194% | 1.448% | 0.9683% | 0.2963% | 0.2963% | 1.177% | 0% | 2.917% | 0.8723% | 4.067% | 1.654% | 1.397% | 1.831% | 0.1% | 1.273% | 2.295% | 0.8372% | 1% | 1% | 0.5987% | 0% | 3.993% | 4.238% | 3.263% | 0.788% | 1.372% | 1.004% | 1.166% | 0.7304% | 0.7846% | 1.062% | 0.52% | 0.3005% | 1.143% | 0% | 0.3088% | 0.5008% | 0.2679% | 0.3923% | 0.3172% | 0.3397% | 0.8514% | 1.104% | 1.005% | 0.7939% | 0.6886% | 0.8973% | 0.5702% | 0.5972% | 0.5814%
Baseline | Q2 April Week 2: 28; Q2 April Week 3: 68; Q2 April Week 4: 108; Q2 May Week 5: 148; Q2 May Week 6: 188; Q2 May Week 7: 228; Q2 May Week 8: 268; Q2 May Week 9: 308; Q2 June Week 10: 348; Q2 June Week 11: 388; Q2 June Week 12: 428; Q2 June Week 13: 468; Q2 July Week 14: 476; Q3 July Week 14: 528.5; Q3 July Week 15: 591.5; Q3 July Week 16: 638.5; Q3 July Week 17: 701.5; Q3 August Week 18: 764.5; Q3 August Week 19: 827.5; Q3 August Week 20: 888.5; Q3 August Week 21: 1137.5; Q3 August Week 22: 1335; Q3 September Week 23: 1524; Q3 September Week 24: 1711.5; Q3 September Week 25: 1900.5; Q3 September Week 26: 2089.5; Q3 October Week 27: 2152.5; Q4 October Week 27: 2278.5; Q4 October Week 28: 2467.5; Q4 October Week 29: 2640; Q4 October Week 30: 2826; Q4 November Week 31: 3015; Q4 November Week 32: 3204; Q4 November Week 33: 3393; Q4 November Week 34: 3582; Q4 November Week 35: 3771; Q4 December Week 36: 3960; Q4 December Week 37: 4149; Q4 December Week 38: 4760; Q4 December Week 39: 5394.5; Q4 January Week 40: 5814.5; Q1 January Week 40: 6185.5; Q1 January Week 41: 6816; Q1 January Week 42: 7439.5; Q1 January Week 43: 8029.5; Q1 January Week 44: 8529; Q1 February Week 45: 8904.5; Q1 February Week 46: 9176.5; Q1 February Week 47: 9388; Q1 February Week 48: 9556; Q1 March Week 49: 9768
Baseline #2 | 28 | 68 | 108 | 148 | 188 | 228 | 268 | 308 | 348 | 388 | 428 | 468 | 476 | 528.5 | 591.5 | 638.5 | 701.5 | 764.5 | 827.5 | 888.5 | 1036 | 1224 | 1413 | 1552.5 | 1741.5 | 1930.5 | 1984.2 | 2068.2 | 2194.2 | 2298.2 | 2499.6 | 2688.6 | 2877.6 | 3007.6 | 3133.6 | 3259.6 | 3385.6 | 3487.6 | 3911.6 | 4334.1 | 4602.2 | 4804.5 | 5091.5 | 5347.32 | 5549.82 | 5758.82 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 5917.92 | 6436 | 6928 | 7412 | 7812 | 8132 | 8419.2 | 8639.2 | 8781.6 | 8861.6 | 8964.8 | 9028.8 | 9060.8 | 9140.8 | 9205.6 | 9320.8 | 9440.8 | 9523.2 | 9603.2 | 9683.2 | 9763.2 | 9768
Baseline % Accu. | Q2 April Week 2: 0.2867%; Q2 April Week 3: 0.6962%; Q2 April Week 4: 1.106%; Q2 May Week 5: 1.515%; Q2 May Week 6: 1.925%; Q2 May Week 7: 2.334%; Q2 May Week 8: 2.744%; Q2 May Week 9: 3.153%; Q2 June Week 10: 3.563%; Q2 June Week 11: 3.972%; Q2 June Week 12: 4.382%; Q2 June Week 13: 4.791%; Q2 July Week 14: 4.873%; Q3 July Week 14: 5.411%; Q3 July Week 15: 6.055%; Q3 July Week 16: 6.537%; Q3 July Week 17: 7.182%; Q3 August Week 18: 7.827%; Q3 August Week 19: 8.472%; Q3 August Week 20: 9.096%; Q3 August Week 21: 11.65%; Q3 August Week 22: 13.67%; Q3 September Week 23: 15.6%; Q3 September Week 24: 17.52%; Q3 September Week 25: 19.46%; Q3 September Week 26: 21.39%; Q3 October Week 27: 22.04%; Q4 October Week 27: 23.33%; Q4 October Week 28: 25.26%; Q4 October Week 29: 27.03%; Q4 October Week 30: 28.93%; Q4 November Week 31: 30.87%; Q4 November Week 32: 32.8%; Q4 November Week 33: 34.74%; Q4 November Week 34: 36.67%; Q4 November Week 35: 38.61%; Q4 December Week 36: 40.54%; Q4 December Week 37: 42.48%; Q4 December Week 38: 48.73%; Q4 December Week 39: 55.23%; Q4 January Week 40: 59.53%; Q1 January Week 40: 63.32%; Q1 January Week 41: 69.78%; Q1 January Week 42: 76.16%; Q1 January Week 43: 82.2%; Q1 January Week 44: 87.32%; Q1 February Week 45: 91.16%; Q1 February Week 46: 93.94%; Q1 February Week 47: 96.11%; Q1 February Week 48: 97.83%; Q1 March Week 49: 100%
Baseline #2 % Accu. | Q3 July Week 16: 61.77%; Q3 July Week 17: 65.89%; Q3 August Week 18: 70.93%; Q3 August Week 19: 75.88%; Q3 August Week 20: 79.98%; Q3 August Week 21: 83.25%; Q3 August Week 22: 86.19%; Q3 September Week 23: 88.44%; Q3 September Week 24: 89.9%; Q3 September Week 25: 90.72%; Q3 September Week 26: 91.78%; Q3 September Week 27: 92.43%; Q4 October Week 27: 92.76%; Q4 October Week 28: 93.58%; Q4 October Week 29: 94.24%; Q4 October Week 30: 95.42%; Q4 October Week 31: 96.65%; Q4 November Week 32: 97.49%; Q4 November Week 33: 98.31%; Q4 November Week 34: 99.13%; Q4 November Week 35: 99.95%; Q4 November Week 36: 100%
Actual Accu. | 0.2922% | 0.7095% | 1.127% | 1.544% | 1.962% | 2.379% | 2.796% | 3.214% | 3.631% | 4.048% | 4.466% | 4.883% | 5.514% | 5.514% | 6.662% | 7.319% | 7.977% | 8.765% | 8.927% | 9.391% | 9.891% | 10.46% | 10.56% | 10.8% | 11.07% | 11.22% | 11.43% | 11.43% | 11.53% | 11.79% | 11.92% | 12% | 12.47% | 14.44% | 15.38% | 16.57% | 18.02% | 18.99% | 19.28% | 19.58% | 20.76% | 20.76% | 23.67% | 24.55% | 28.61% | 30.27% | 31.66% | 33.49% | 33.59% | 34.87% | 37.16% | 38% | 39% | 40% | 40.6% | 40.6% | 44.59% | 48.83% | 52.09% | 52.88% | 54.25% | 55.26% | 56.42% | 57.15% | 57.94% | 59% | 59.52% | 59.82% | 60.96% | 60.96% | 61.27% | 61.77% | 62.04% | 62.43% | 62.75% | 63.09% | 63.94% | 65.05% | 66.05% | 66.84% | 67.53% | 68.43% | 69% | 69.6% | 70.18%
Variance | -0.005503% | -0.01337% | -0.02123% | -0.02909% | -0.03695% | -0.04481% | -0.05267% | -0.06054% | -0.0684% | -0.07626% | -0.08412% | -0.09198% | -0.6413% | -0.1039% | -0.6067% | -0.7828% | -0.7952% | -0.938% | -0.4558% | -0.2946% | 1.754% | 3.208% | 5.043% | 6.722% | 8.388% | 10.17% | 10.61% | 11.9% | 13.73% | 15.24% | 17.02% | 18.87% | 20.33% | 20.3% | 21.3% | 22.04% | 22.52% | 23.49% | 29.45% | 35.65% | 38.77% | 42.57% | 46.11% | 51.62% | 53.59% | 57.05% | 59.5% | 60.45% | 62.52% | 62.96% | 62.84% | [20 empty] | 0% | 3.848% | 8.492% | 13.13% | 16.89% | 19.31% | 21.15% | 22.39% | 23.06% | 23.19% | 23.35% | 23.43% | 23.16% | 23.4%
Current week highligter | Q3 July Week 16: 100%
Civil Works Availability and Manpower Shortage